## 2013 Directions
2013 DESIGN & CONSTRUCTION REVIEW PROCESS
For 4% LIHTC/Bond Properties
Last updated: 9/18/14
In order to ensure compliance with Georgia DCA’s Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits. As such, the project team is required to submit documents to DCA throughout the design and construction process for review.
It is the strict policy of DCA that all applicants will be held to all representations made in the OAH 2013 Core Application Form and all supporting documentation for the duration of the greater of either the Credit Compliance Period or term of the HOME loan. Any material project changes after submission of Application to DCA must be approved in writing by DCA prior to the change. Failure to obtain the appropriate approvals can result in unfavorable compliance scoring or the recapture of credits.
All design/construction submittals must be accompanied by the 2013 4% LIHTC/Bond Design & Construction Transmittal (Transmittal Form). The Transmittal Form provides program-specific deadline dates and document requirements. Documents may be submitted earlier than the deadlines. Do not submit documents piecemeal. DCA will not begin its review until all documents required for a particular stage have been submitted.
All extension requests must be submitted in writing to: Michael Collins, Architectural Services, michael.collins@dca.ga.gov, (404) 679-4898
NO LATER THAN 30 DAYS PRIOR TO APPLICATION SUBMISSION
One hard copy and one electronic copy of the documents must be submitted. See additional directions below. The following must be submitted no later than 30 days prior to the submission of the Application:
1. 2013 4% LIHTC/Bond Design & Construction Transmittal
2. Qualifications for 3rd party cost reviewer (ONLY contractor identity of interest)
3. Architectural Waivers & Amenities/Design Options Pre-Approval
APPLICATION
At the application stage, projects must submit all application documents in the formats detailed in the 2013 Core Application Instructions, QAP, and Architectural Submittal Instructions manual.
NO LATER THAN 30 DAYS AFTER APPLICATION SUBMISSION
One hard copy and one electronic copy of the documents must be submitted. See additional directions below. The following must be submitted no later than 30 days after the submission of the Application:
1. 2013 4% LIHTC/Bond Design & Construction Transmittal
2. Permit drawings (see directions for definition of “permit drawings”)
3. Specifications
4. Drawing Log (see DCA form)
5. Qualified accessibility consultant's plan review comments
6. Schedule of values (see DCA form)
7. Contractor Qualification package
8. Federal Work Authorization (E-Verify) Affidavits
9. Written verification of compliance with energy code
10. 3rd party cost review report (ONLY contractor identity of interest)
AT CONSTRUCTION COMMENCEMENT
1. 2013 4% LIHTC/Bond Design & Construction Transmittal
2. "For Construction" drawings, specifications, & updated drawing log
3. Notice to Proceed
4. Executed Owner/Contractor Agreement
5. Finalized construction schedule
6. Building Permits
Requirements for Paper Submissions
One binder containing all necessary forms and supporting documentation according to the Transmittal Form and separated by numbered dividers in the order determined by the Transmittal Form.
The binder must be clearly labeled with the DCA project number and name on the front cover.
Permit and Construction drawings must be printed in half-size, scalable format. These must be bound separately from the binder.
Requirements for Electronic Submission
One VIRUS-FREE USB flash drive in a small, protective re-sealable container with a built-in fastener - e.g., Velcro, zipper, Ziploc, string or metal clasp - containing exact electronic copies of all of the same items described above, arranged in the same order. DO NOT ATTEMPT TO EMAIL THESE FILES.
Upon opening the flash drive/CD, the following items organized by section number, DCA project number, and document description, corresponding to the Transmittal Form, must be visible:
For example, 30 days prior to application:
01 13-0xx Transmittal Form
02 13-0xx Cost Reviewer Qualifications
03 13-0xx Waivers and Pre Approvals
04 13-0xx Other
For example, 30 days after application:
01 13-0xx Transmittal Form
02 13-0xx Permit Drawings
03 13-0xx Specifications
04 13-0xx Drawing Log
05 13-0xx Accessibility Plan review
06 13-0xx Schedule of Values
07 13-0xx Contractor Qualifications
08 13-0xx E-Verify
09 13-0xx Compliance with Energy Code
10 13-0xx Cost Review
11 13-0xx Other
1. Where a section contains multiple documents or pages, a folder must be created into which all files are loaded.
2. Please do not create additional subfolders.
3. If a section will be empty, include NA at the end of the section name.
4. Double-check the flash drive. Verify that it contains all required files and that it operates properly.
5. Electronic submissions of Schedule of Values must be in Excel format.
6. Electronic drawing files must be labeled, at minimum, with the drawing page number which corresponds to the Drawing Log.
7. Drawings must be in PDF format.
8. One project submission per flash drive. The flash drive must be of a sufficient size to contain all files that will be submitted
9. Both the small, protective re-sealable container and the external casing of the flash drive itself must be labeled with the DCA project name and number.
Mailing Instructions
DELIVER TO:
Attn: Construction Manager
Office of Affordable Housing – Architectural Services
Georgia Department of Community Affairs
60 Executive Park South NE
Atlanta, Georgia 30329-2231
Additional Policies
Definitions
1. Permit drawings: drawings that will be submitted to the local building authority to obtain the permit for construction
2. For Construction drawings: drawings that have incorporated local building authority comments from the permitting process, syndicator and/or lender review, DCA review, accessibility consultant review, and all other consultant's design comments (green building, historic preservation, etc.)
Identities of Interest
If an identity of interest exists between any Project Participant and the contractor, a third-party cost review must be conducted. For HOME projects, the third-party cost review will be ordered by DCA upon submittal of the Schedule of Values. For tax credit only projects, the qualifications of the proposed third-party reviewer must be submitted to DCA before the review is conducted.
The required qualifications are as follows: the consulting firm must have completed three (3) or more Architecture/Engineering Reviews and Cost Estimate Reviews for lenders pursuant to the HUD MAP (multifamily accelerated processing) program for the Atlanta Multifamily Hub since 2008. Consideration may be given to firms that have similar experience with other HUD Multifamily Hub offices. Consideration will also be given to firms that have prepared a review for a project that has HUD funding in conjunction with Low Income Housing Tax Credits.
Requests for consideration must contain, at minimum:
(1) Resumes of firm team members that will conduct the review;
(2) Description of relevant past work conducting architecture/engineering reviews and cost estimate reviews for HUD and Low Income Housing Tax Credit projects (project list);
(3) A (sample) copy of a cost estimate review performed for the HUD MAP program.

## 2013 4% Bond Pre Constr
|  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  |  | 4% TAX CREDIT & BOND
Office of Housing Finance and Development Division
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2013 4% LIHTC/BOND DESIGN & CONSTRUCTION - PRE CONSTRUCTION TRANSMITTAL
*** THIS FORM SHALL ACCOMPANY ALL SUBMITTALS TO ARCHITECTURAL SERVICES DEPT FOR REVIEW***
OWNER/DEVELOPER CONTACT FOR DESIGN/CONSTRUCTION REVIEW | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT DESCRIPTION
| A. | Unit Descriptions |  | # of units | E. | Unit Square Footage
|  | New Construction |  |  |  | Total Gross Residential Square Footage
|  | Adaptive Reuse |  |  |  | Total Gross Common Space Square Footage
|  | Rehab |  |  |  | (community buildings/community rooms, hallways, amenity spaces)
|  | Historic Rehab |  |  |  | TOTAL GROSS PROJECT SQUARE FOOTAGE |  |  |  |  | 0
| B. | Total Residential Units |  |  | F. | Buildings
|  | Common Space Units |  |  |  | Number of Residential Buildings
|  | Total Units |  |  |  | Number of Non-Residential Buildings
Total Number of Buildings
| C. | Unit Mix
|  | describe # of bedrooms & baths in each unit |  |  | G. | Tenancy: | Family or Senior
[5 empty] | H. | Accessibility
[6 empty] | Mobility Impaired Units |  |  |  | at least 5% of total units
| D. | Acreage |  |  |  | list unit #s for mobility units
|  | Gross Acreage |  |  |  | Sight / Hearing Impaired Unit |  |  |  | at least 2% of total units
|  | Developed acreage |  |  |  | list unit #s for site/hearing impaired units
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DUE NO LATER THAN 30 DAYS PRIOR TO APPLICATION SUBMISSION
Qualifications for 3rd party cost reviewer (ONLY contractor identity of interest)
Architectural Waivers & Amenities/Design Options Pre-Approval
DUE NO LATER THAN 30 DAYS AFTER APPLICATION SUBMISSION
Permit drawings & specifications
Drawing Log (see DCA form)
Qualified accessibility consultant's plan review comments
Schedule of values (see DCA form)
Contractor Qualification package (see page 42 of 52 of the 2013 Threshold QAP)
Federal Work Authorization (E-Verify) Affidavits (see DCA form)
Written verification of compliance with energy code
3rd party cost review report (ONLY contractor identity of interest)
<< Other - describe here >>
DUE AT CONSTRUCTION COMMENCEMENT | [6 empty] | Other Transmittals Enclosed/Comments:
"For Construction" drawings, specifications, & updated drawing log
Notice to Proceed
Executed Owner/Contractor Agreement, including all attachments & appendices
Finalized construction schedule
Building Permits
Forms available at: http://www.dca.ga.gov/housing/housingdevelopment/programs/architecturaldesignandconstruction.asp

## 2013 4% Bond Constr Admin
|  |  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  | 4% TAX CREDIT ONLY
Office of Housing and Finance
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2013 ARCHITECTURAL SERVICES - CONSTRUCTION ADMINISTRATION TRANSMITTAL (form date: 09.18.14)
OWNER/DEVELOPER CONTACT CONSTRUCTION ADMINISTRATION | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT SCHEDULE | [6 empty] | UNIT INFO
| A. Notice to Proceed |  |  |  | C. First Residential Bldg "Placed In Service" |  |  | A. Number of Units
|  | Date: |  |  |  | Estimated Date: |  |  | New Construction:
[6 empty] | Actual Date: |  |  | Rehab Construction:
| B. Commencement |  |  |  | D. Substantial Completion (AIA Certif. of Sub. Compl.) |  |  |  | Total Units: | 0
|  | Date: |  |  |  | Estimated Date:
Actual Date:
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
COMMENCEMENT SUBMISSION (due prior to construction commencement)
Notice to Proceed
Finalized construction schedule
Permits (Land Development, Building,,,)
Other:
DCA FINAL INSPECTION SUBMISSION (due when final retainage release pay app is issued)
Request For Final Construction Compliance Form
Final Inspection Fee ($3,000)
Certificates of Occupancy (COs)
DCA Placed In Service form
AIA G704 Certificate of Substantial Completion
Final Contractor Application & Certificate for Payment(s) (100% release of retainage)
Satisfactory completion of final accessibility inspection with confirmation of resolution of any outstanding issues stemming from the inspection
--include all site inspection reports performed by accessibility consultant (minimum three per QAP)
--include a letter from the Consultant or Architect stating all reported accessibility concerns have been resolved
DCA Amenities and Design Options Re-Certification
Other:
ARCHITECTURAL 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources)
Proof of Compliance with Georgia State Minimum Standard Energy Code
Green Building certifications (when applicable)
Verification from a qualified HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP requirements (when project is "not seeking" a grn bldg cert.) certification
Radon Testing that demonstrates levels below the EPA recommended limits
--include a radon report from radon professional
--include a radon tests
Verification of compliance with each DCA Letter of Determination "Condition of Funding" (Architectural Dept)
--provide a narrative that describes means of compliance with each Conditions of Funding (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
Contractor Cost Certification (when there is an Identity of Interest between any Project Participant and the General Contractor)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
iv: Complete subcontractor log:
Other:
OTHER SUBMISSIONS
Other:
Other:
Forms available at: http://www.dca.ga.gov/housing/housingdevelopment/programs/architecturaldesignandconstruction.asp
Note on A23: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA Final Inspection Submission: Package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request).
Note on A32: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA Final Inspection Submission: Package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request).
Note on B34: 2013 QAP-CORE: SECTION 14. POST AWARD DEADLINES F. Completion of Work Scope.* DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated. At its sole and absolute discretion, DCA may approve modifications to the proposed work scope upon written request. 2013 QAP-CORE: SECTION 14. POST AWARD DEADLINES F. Completion of Work Scope.* Owners of projects receiving Credits in the 2013 round for the rehabilitation of an existing property must perform 100% of the work scope in accordance with the original physical needs assessment submitted with the Application no later than December 31, 2015. Owners of properties receiving Credits for new construction in the 2013 round must perform 100% of the work scope as set forth in the DCA approved construction drawings and specifications no later than December 31, 2015. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2015. Temporary Certificates of Occupancy that prohibit occupancy or condition occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated. DCA may approve modifications to the proposed work scope upon written request.
Note on B35: 2013 State of Georgia Qualified Allocation Plan-EXHIBIT A Final Inspection Fee (for all LIHTC properties, both 4% and 9%, excluding those projects involving HOME funds) 9% Deadline Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed 4% Deadline Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed NOTE: Include a copy of the check
Note on B36: 2013 Architectural Manual - Architectural Submittal Instructions - F. Documents due before final allocation of resources: 8. Certificates of Occupancy allowing immediate use of buildings and units prior to or on the application deadline. To meet IRS and DCA requirements, and in jurisdictions not issuing Certificates of Occupancy, the Owner shall obtain from the authority having jurisdiction a letter affirming that the property meets all code requirements. 2013 QAP-CORE: SECTION 14. POST AWARD DEADLINES - F. Completion of Work Scope. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2015. Temporary Certificates of Occupancy that prohibit occupancy or condition occupancy will not be accepted to meet this requirement.
Note on B37: 2013 QAP-CORE: SECTION 14. POST AWARD DEADLINES - G. Placement-In-Service. Owners of projects receiving Credits in the 2013 round must place all buildings in the project in service by December 31, 2015. 2013 Qualified Allocation Plan - Core EXHIBIT A DCA Placed In Service Form Fees NONE 9% Deadline Within 30 days of the 1st building placed in service 4% Deadline Within 30 days of the 1st building placed in service
Note on B38: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B40: 2013 QAP-Threshold : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The consultants must perform a pre-construction plan review and inspect the project at least 3 times during construction, presumably to monitor grading operations, framing, and final compliance. DCA must be copied on all reviews/reports.
Note on B43: DCA Amenities and Design Options Re-Certification: This form should be completed to reflect the Threshold items which the team noted in their application. The document should also reflect any project changes (Project Concept Changes,,,).
Note on A46: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA 8609 Clearance Submission: Package should be submitted to the attention of the DCA Construction Administration prior to the Owner's request for the 8609.
Note on B48: 2013 QAP THRESHOLD-XVII. BUILDING SUSTAINABILITY: Compliance with Georgia State Minimum Standard Energy Code (International Energy Conservation Code with Georgia State Supplements and Amendments) in effect at the time of permit issuance. Proof of compliance must be submitted prior to release of 8609s.
Note on B50: 2013 QAP-THRESHOLD-XVII. BUILDING SUSTAINABILITY-B. Measured duct and building envelope leakage. Verification by certified HERS rater of a HVAC system duct leakage rate and dwelling unit air infiltration rate that meets or exceeds the Energy Star Qualified Homes, Version 3 National Program Requirements for the appropriate project specific climate zone (the duct leakage rate for all climate zones in Georgia is < 4 cfm/100 square feet; dwelling unit air infiltration rate to outdoors for climate zone 2 is an ACH 50 of 6 and for climate zones 3 and 4 is an ACH 50 of 5). Verification testing must follow the Energy Star testing protocol. If the project is "not seeking" a green building certification, test reports verifying compliance must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes first. Projects that plan to utilize Packaged Terminal Air Conditioners (PTAC’s) or ductless mini-splits for all units are exempt from the duct leakage requirement.
Note on B51: 2013 Architectural Manual-F. Documents due before final allocation of resources: 6. Radon testing that demonstrates levels below the EPA recommended limits 2013 Environmental Manual: B. Non-Scope Issues for Phase I Reports - 7. Radon Gas a. If the Applicant’s project involves the "renovation" or use of an existing structure, a radon "test" must be performed to determine radon gas levels, unless an EPA approved short-term radon test has been performed in the lowest public areas of the building(s) within the last six months which demonstrated radon levels at or below 4 pci/l or 0.02 WL. A copy of the Radon Report should be attached to the Phase I Report. Any readings that exceed the EPA limits must mitigate radon levels are part of the work scope in accordance with ASTM E2121 - 08 Standard Practice for Installing Radon Mitigation Systems in Existing Low-Rise Residential Buildings. b. If the Applicant’s project involves "new construction", the building(s) must be constructed in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 - 08 Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings and the buildings must be "tested" for radon upon completion of construction. c. The minimum requirement for testing locations is one test per every 2000 square feet of ground-contact units. However, radon concentrations can be highly localized and best practice for radon testing should involve a certified radon tester (http://www.radongas.org/ or http://www.nrsb.org/). In addition, it is recommended that at least one test be located in each building on each floor above the ground-contact level, covering a minimum of 10% of the units on all floors above the ground floor.
Note on B54: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GADCA "Letter of Determination" Conditions of Funding. Restate each "condition of funding" verbatim from the Letter of Determination letter before each response describing method of compliance. Provide supporting docs/evidence as needed.
Note on B57: 2013 QAP-Core: Exhibit A to Appendix I: DCA UNDERWRITING POLICIES - 11.Identity of Interest. DCA will require that a contractor cost certification be submitted where there is an identity of interest between any "project participant" and the "general contractor". The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification “Project Participants” mean the Owner, Developer, Management Company, Consultants and Syndicator for a project for which an Application is submitted.