## Slide 1: YOUR 2016 CDBG Grant Administration & Financial Management
  Brent Allen – Cindy Alligood
October 6, 2016
$?$?$?

## Slide 2: What We Will Cover…
Grant Award Package
Your CDBG Bank Account
CDBG Compliance with Your Field Rep
Start-Up, Citizen’s Participation & Fair Housing
Procurement
Financial Management
Closeout
Grant Amendments
Reporting Requirements

## Slide 3: GRANT AWARD PACKAGE
1. Statement of CDBG Award
2. Budget Summary
3. General & Special Conditions
4. Statement of Revisions
5. Civil Rights Compliance Certification
6. Authorized Signature Card
7. VENDOR MANAGEMENT BANK ACCOUNT Form
(Chapter 1)

## Slide 4: 1. STATEMENT OF CDBG AWARD
Your CONTRACT with DCA
Your unique GRANT #. Include GRANT # on ALL forms & correspondence to DCA
GRANT PERIOD: An Important Timeline to Keep
Sign & Return WHITE COPY to DCA
KEEP COPY FOR YOUR FILES
Notes: First Bullet: “in accordance with the plan set forth in the application
Second Bullet: on ALL correspondences submitted to DCA
Third Bullet: If an extension is needed, request in advance of the grant expiration.

## Slide 5: 2. BUDGET SUMMARY
Your Official Budget
Use THIS budget (not application’s) to create your ledger, accounting records
Local match/leverage is listed at bottom; keep documentation of it – it will be monitored
DO NOT SIGN & RETURN this form w/award package

## Slide 6: 3a. GENERAL CONDITIONS
For ALL CDBG awards
Includes standard, mandatory CDBG compliance responsibilities (Environmental, Section 3, Conflict of Interest, etc.)
Must be signed & returned in award package
Notes: Second bullet: this goes back to that contract idea: by signing, you are agreeing to these General Conditions.

## Slide 7: 3b. SPECIAL CONDITIONS
Specific to each CDBG Award
Elected Official’s Signature = “I agree to clear these conditions ASAP.” (See General Conditions)
Not cleared until you receive a “Grant Adjustment Notice” (no clearance, no $$$)
Must be signed & returned in award package
Notes: First Bullet: you may not have any SC’s

## Slide 8: 4. STATEMENT OF REVISIONS
Your Statement of Award might say, “This award is subject to revisions” →
Changes to proposal were made (usually budget)
Review thoroughly, sign & return with award package

## Slide 9: 5. CIVIL RIGHTS COMPLIANCE
Complete the form
Explain any civil rights complaints
Preparer of form plus Chief Elected Official should sign
Return with award package

## Slide 10: 6. AUTHORIZED SIGNATURE CARD
Local authorization to sign & submit draws
Gives option of 1 or 2 signatures on draws
At least one local government signature is required (employee or official)

## Slide 11: 7. Vendor Management Bank Account Form
Draw-Down funds deposited electronically to your CDBG bank account
Must be signed & returned with award package
Attach an original Voided Check

## Slide 12: IMPORTANT FINAL REMINDERS
Keep copies of your entire award package
Sign & Return Award Package by November 10, 2016
Remember: No Signed Award Package = No $$$
Notes: *Not the budget summary

## Slide 13: Draw-Downs to CDBG Checking Account
DCA processes draws on Tuesdays & Thursdays
Time your draw-downs accordingly; “funds should be in your bank 7 days from the day DCA processes request”
Match signatures to those on Authorized Signature Card
Funds should be paid out of your account no later than 3 business days after they are deposited

## Slide 14: You cannot Draw Down funds until you…
Complete and submit grant award package to DCA
Clear your special conditions through GAN’s
Receive DCA environmental clearance for non-exempt activities
…are caught up on Quarterly Reports
Verify required cash match/leverage (for final draw down)

## Slide 15: YOUR CDBG BANK ACCOUNT
Separate, non-interest bearing bank account for each CDBG award
Account is for CDBG $$$ ONLY (no match or any other project funds!!!!!!!!)
Tips:
  Check with bank for minimum balance; if local $ is used to open, it can be reimbursed later
  CDBG will not pay insufficient fund charges
  CDBG funds-on-hand for over three-business days should be limited to $5,000 or less. If more than $5,000….you must send it back to DCA.
Notes: *except, of course, when you draw down funds. Drawn down funds should leave account within 3 days of arrival

## Slide 16: CDBG Compliance with Your Field Rep (Chapter 1: Section 4)

## Slide 17: CDBG Compliance with your Field Rep
Your responsibility is to…
Keep project on schedule
Stay on top of Quarterly Reports, Draw-Downs, Special Conditions…all can create delays
Expect monitoring from your Field Rep at least once every 6 months
Communicate problems/delays on your QR’s and to your Field Rep
Violations will result in sanctions (see Ch.1, section 15)

## Slide 18: Your Field Rep’s Project Review Checklists are in APPENDIX 2…
These are the forms we use when we visit
Use them as a cheat-sheet to prepare for monitorings
Ask in advance what we will be looking for
Notes: These are the forms we use when we monitor your records! This is excellent insider information which will prepare you for these visits.

## Slide 19: START-UP SITE VISIT
Within 60 Days of Grant Award
Elected Official
City or County Clerk
Grant Administrator
Interested Parties
Low/Mod Surveys
START-UP SITE VISIT

## Slide 20: Monitoring Site Visits
Your Field Rep will and the public might request to see…
The CDBG Application
Citizen Participation plan
Financial records - including QR’s, bank statements, invoices, & bank register showing receipts & disbursements in chronological order (i.e., CDBG Check Book)
Environmental Review Record
Other pertinent information such as engineering plans or floor plans

## Slide 21: Citizen’s Participation (Ch. 1, Sec. 8)
Mandatory Public Hearings*
  Prior to application submission (“pre-award PH”)
  Within 60 days of Grant Award Date (“post-award PH”)
  At time of Project Completion (“close-out PH”)
  Plus a PH only if CDBG program is amended
  * See sample PH notices in Appendix 1
Notes: Program jargon at DCA

## Slide 22: Citizen’s Participation, cont.
Public Hearing Protocol
A full 5 CALENDAR DAYS must pass from publication date to public hearing date.
DO NOT count publication date or public hearing date as part of the 5
DO NOT publish in legal section
Location must meet Title 2 accessibility standards
Complete the Sec 504 DCA Meeting Checklist

## Slide 23: Citizen’s Participation, cont.
Things to Remember…
Both handicap & foreign language accessible
Post-Award PH Must be held within 60 days of award (by December 6th)
Notify your Field Rep at least 1 week in advance of close-out public hearing
A Good Idea: why not schedule your PH’s in tandem with Start-Up & Close-Out Monitorings?

## Slide 24: Recipients are obligated to Affirmatively Further Fair Housing
Resolution supporting State/Federal FH Law
Public Information Campaign on FH
FH Discussion on Public Hearing Agenda
Distribute FH brochures at public meeting
Post FH Posters at City/County Buildings
Provide FH info to relocatees, if applicable
See new Fair Housing Equal Opportunity Review monitoring checklist
Notes: Posters can be found on HUD website or they can be e-mailed to you upon request

## Slide 25: Affirmatively Furthering Fair Housing/Section 3
Make sure procedures are in place to notify Section 3 residents and businesses about employment, training, and contracting opportunities
Keep documentation of all efforts including notifications of any hiring opportunities
Provide Resident Certification and Affidavit forms for employment
Bid ads must convey that the contract is a Section 3 covered contract
Notes: Posters can be found on HUD website or they can be e-mailed to you upon request

## Slide 26: Affirmatively Furthering Fair Housing/Section 3
A Pre-Bid meeting or workshop is required
Include all Section 3 clauses in all applicable contracts
Post a location and phone number of person to contact and how to apply for employment, training, or contracting opportunities at the job site
Notes: Posters can be found on HUD website or they can be e-mailed to you upon request

## Slide 27: Procurement
“ALL procurement transactions will be conducted in a manner providing full & open competition.” (Ch. 3, Sec. 4[c])

## Slide 28: Procurement
We will discuss three types of procurement:
Small Purchases < $100K
Professional Services from the Private Sector (grant administrator, engineer, architect)
Public Works Construction
For Your Reference:
--Chapter 3, Section 4
--Appendix 2
  2 CFR 200, Subpart D, Procurement Standards
  CONFLICT OF INTEREST REGULATIONS
  Georgia Local Government Public Works Construction Law

## Slide 29: Procurement, cont.
AVOID CONFLICTS OF INTEREST WITH OFFICIALS AND STAFF
Applies to Procurement of ALL goods & services
Officials & Staff should not benefit from CDBG by
  Having a financial interest
  Receiving a direct program benefit
  Having family or business ties to CDBG project
NO EXCEPTIONS with a Procurement C.O.I.
Much more detail to come (see Steed Robinson Presentation from this Workshop)
Notes: This is a very big deal. There are different types of COI, some of which can receive exceptions. If it’s discovered that a Mayor’s nephew is living in a target area, for example, then as long as certain strict steps are taken to disclose this fact, DCA can potentially grant an exception. Not the case with Procurement. If the Mayor’s nephew is hired on as a contractor in a project using CDBG funds, for example, then there will be serious consequences.

## Slide 30: Procurement, cont.
Type # 1: Small Purchases < $100K
Bargain Shop
Get price quotes from several (three) different qualified sources (remember, full/open competition)
Keep documentation in file
This method cannot be used for Professional Services

## Slide 31: Procurement, cont.
Type # 2: Professional Services
“Competitive Negotiations”
Advertise RFP or RFQ (include “evaluation factors”) in newspaper and/or “publication with adequate circulation & exposure”.
Request proposals via U.S. Mail or email from “known providers” (at least 7 for grant admin; at least 10 for engineer or architect)
Allow minimum of 30 days response time
KEEP DOCUMENTATION (ads, mail receipts, etc.)

## Slide 32: Procurement of Prof Services, cont.
Prepare written evaluation plan with method for scoring proposals
EXAMPLE:
Evaluation Factor #1
“Grant administrator’s knowledge of CDBG guidelines and regulations”.
Score range 4, 3, 2, 1, 0
4 points = 5 or more years of training
3 points = 3-4 years of training
2 points = 2 years of training
1 point = 1 year of training
0 points = less than 1 year of training

## Slide 33: Procurement of Prof Services, cont.
FINAL NOTES:
Include Evaluation Factors in RFP/RFQ
Scoring involves Elected Officials & Staff
After evaluating/scoring, notify legal counsel & obtain official approval from Council or Commission
If Procurement of Prof Services process was correctly conducted within the last two years for an application denied within the past year, a new procurement process is not necessary to retain same firm (if same project and Section 3 has been followed).
KEEP RECORDS of all required actions – it will be monitored (ads, mail-outs, evaluations).
Notes: #1. In other words, service providers should know what you’re looking for and you should establish these criteria prior to soliciting the service
#3. Say if you went through procurement in order to get Bonus Points in 2009 but didn’t get funded

## Slide 34: Procurement of Public Works Construction
Advertise for “Competitive Sealed Bids”
Traditional “Design-Bid-Build” model vs. Non-Traditional “Design-Build” or “Construction Management” models
If non-traditional, you must first consult with Legal Counsel & DCA
Reference Appendix 2
  Georgia Local Government Public Works Construction Law
  2 CFR 200, Subpart D, Procurement Standards

## Slide 35: Procurement of Public Works Construction, cont.
What’s Included in the Bid Advertisement?
Work hand-in-hand with engineer/architect to prepare complete & specific CDBG project description
Seek a “firm-fixed price” contract
Selection of winner is “principally based on price”
Must include mandatory bonding requirements, pre-qualifications, pre-bid conferences & contract is a Section 3 covered contract & contract is a Section 3 covered contract
All bids must be opened publicly at time & place specified in bid ad
Notes: “Firm-fixed-price” is a must for these contracts, compared to “cost plus % of cost” method.

## Slide 36: Procurement of Public Works Construction, cont.
The Bid Advertisement, cont.
Include Alternates to the “Base Bid”
  “DEDUCTS” (you’d prefer to keep but can do without)
  “ADD’S” (non-essential but you’d like to have)
List them by priority because…
  When bids come in too close to call, these can make difference in determining lowest bidder
  It levels playing field for pool of contractors
  Addresses “change-order” issues in advance
Notes: “Base Bid” plus or minus… When going out to bid, the community might include items in the bid that they could do without but they would really like to have if within their budget; i.e. architectural shingles, metal roof, shock resistant exercise floor and/or porch (senior centers), etc. Works the same way with deducts; i.e. brick facade or four-side brick, etc.

## Slide 37: Procurement of Public Works Construction, cont.
Bid Advertising Requirements
Advertise in newspaper at least twice in four-week period prior to bid opening. Or on Internet website (see below).
Post construction opportunity at local government office.
Advertising Options:
“Legal Organ” (newspaper)
  1st ad “at least 4 weeks prior to the opening of the sealed bids or proposals”
  2nd ad “shall follow no earlier than 2 weeks from the first advertisement”
Internet
  Must run at least 4 consecutive wks continuously prior to bid opening on local gov website or other site “identified by the governmental entity”. Must document with hard copies showing dates for 4 weeks.
Notes: Quotes from the GA Local Gov Public Works Construction Law, Appendix 2. If you go the internet route, make sure to print out documentation. Regarding the 2nd newspaper ad, use common sense. You don’t want to run this ad only one day before the bid opening…the point is to advertise MORE THAN ONCE and to give potential contractors TIME to respond. If the first ad is 4 weeks before the bid opening (minimum), then make the 2nd ad two weeks later in order to provide sufficient time to the contractors who might not have seen the first advertisement. If they only see the 2nd ad, they will have a full two weeks to respond.

## Slide 38: Procurement, cont.
If bids come in really low or too high, formally request DCA approval to:
  Change Project Scope (increase or decrease)
  DCA reserves right to approve or reject
If you only get one bid for contract (professional service or construction)
  It’s called “non-competitive” or sole source procurement (Ch. 3, Section 4)
  You must request DCA’s “sole source approval” by providing:
    Advertisement documentation, dates
    Response date
    List of firms who received solicitation
  Wait to receive DCA letter before proceeding
Notes: DCA reserves the right

## Slide 39: Procurement, final
Contracts paid with CDBG $
Administrative Contract Requirements see Ch. 1 Section 18
For all contracts paid with CDBG $:
  Appendix 2 → Project Review Checklists →
  #4 Procurement Review
  #16 “Procurement Review for Public Works Construction”
Matrix is key to required clauses & bonds for your contracts
All contracts should include compensation amount (“firm-fixed price”)

## Slide 40: FINANCIAL MANAGEMENT

## Slide 41: Financial Management
Required Cash Match
Formula: None required up to $300,000
5% for grant between $300,001 & $500,000
10% for grant portion $500,001 & up
CDBG Housing-only awards exempt from Match
LEVERAGE
In your application, you told DCA you would contribute (cash and/or in-kind) toward the completion of the project. DCA gave you “leverage” bonus points for this commitment.
PLEASE NOTE: Field Rep must review CASH MATCH and LEVERAGE prior to processing of final draw down!
Chapter 1; Section 4.
“……field representative to make a recommendation regarding payment of the final CDBG draw in light of progress toward meeting leverage requirements. Match and leverage will again be reviewed/verified at the closeout site visit.”
Refer to BUDGET SUMMARY in grant award package.

## Slide 42: Financial Management, cont.
“Unallowable Interest” and “Program Income”
Remember, CDBG funds must be deposited into a “non-interest bearing” checking account only! CDBG funds SHOULD NOT EARN INTEREST. Grant funds should be drawn down AS NEEDED and should be expended within 3-business days.
If the CDBG generates $, you have to return it to DCA. Or apply Program Income $ toward the project, thus, reducing the amount of CDBG funds drawn on the project.
  See Ch.3, Section 3 for income examples
Exception to that Rule:
CDBG Revolving Loan Fund (typical with Econ Dev)

## Slide 43: Financial Management, cont.
Quarterly Reports
Due 30 days after end of each Qtr (4/30, 7/31, 10/31, 1/31*)
Failure to comply = No $ Draw Down
Provide “contract” information
Fill out Narrative Section WELL. Discuss progress made and problems encountered.
Check “Final” QR only after all activities & expenditures are complete & beneficiaries recorded

## Slide 44: Financial Management, cont.
Audit Requirements (Ch. 3, Section 2)
“Must contract for annual independent audit” and submit to DCA
  If Recipient spend $750K or more in total Federal funds (CDBG plus other)…
    Follow 2 CFR 200, Subpart D, Procurement Standards
  If $750K or less in total Federal funds…
    Recipient is exempt from Federal Audit requirements but not from State Audit Requirements
    QUESTIONS? Contact Pam Truitt (404) 679-5240 or pam.truitt@dca.ga.gov

## Slide 45: Close-Out
Your field Rep will need to see the following:
  Final Public Hearing documentation
  Final Quarterly Report
  Final Wage Compliance Report
  Actual Accomplishments form
  Surveys & Beneficiary Data
This will result in “Conditional Closeout” Letter

## Slide 46: Closeout, cont.
After audit requirements satisfied, you will receive “Final Closeout Letter”
Retention of Records (Ch. 1, Section 10)
  Retain for at least 3 years after Final Closeout Letter

## Slide 47: Immediate Action Items:
COMPLETE & RETURN grant award package by November 10th!
SCHEDULE & HOLD post-award public hearing within 60 days of award (by December 6th, notify field rep).
OPEN non-interest bearing checking account.